## Apr 2016
Date | Hour | Notes
Total | 20.5
2017-02-01 | 3 | Generate TDMv3 BLE cable replacement profile. Program MCU to communicate with BLE. Some hardware failure, contacted Bluegiga.
2017-02-04 | 4.5 | Get key from Bluegiga. Start implementing BLE cable replacement profile. Device detected, connected, see data but not as expected.
2017-02-05 | 3.5 | Debug. Data is as expected, add upgrade through UART support. Add BUS_ID.
2017-02-07 | 3.5 | Make BUS_ID read/write, save to flash.
2017-02-13 | 4.5 | Customer site meeting, demo, get feedback. Code change according to customer feedback.
2017-02-25 | 1.5 | Customer reports I2C read back all 0 happens randomly. Port code to TDMv3, add debug code, run over the weekend, no I2C read error.