## Apr 2016
Date | Hour | Notes
Total | 24.5
2016-10-20 | 1 | Read TDM schematic, ST_LIS3DSH datasheet, ST_L3GD20H datasheet
2016-10-21 | 2 | Keil development environment installed for last project was for STM32L0 and F0 only. Re-install Keil MDK Lite, which supports STM32F3, but with code size limit to 32K. Create project using ST CubeMx, compile OK, code sizw 11K.
2016-10-23 | 7 | Add GPIO functions. Add I2C device driver for sensors ST_LIS3DSH and ST_L3GD20H. Add SPI SD card driver. Sensors are read OK through I2C but SD card doesn't respond. Tried different SPI settings and different SD card config, still no respond from SD card.
2016-10-26 | 3 | Struggling with SD card communication.
2016-10-27 | 1 | Tried an old 2G SD card and it works! Same code not work with the 16G card comes with TDM board.
2016-10-29 | 7 | Sensor data format. ST_LIS3DSH has X, Y, Z all 16 bit signed integer, meter per square second, devid it by 100 to get the real value. ST_L3GD20H has X, Y, Z all 16 bit signed integer, degree per second, devid it by 100 to get the real value. 12 bytes per read (10 ms), 42 reads in a SD data block (512 bytes 420 ms). 1GB will be able to last 24 days. Add LED for running state. Add USB CDC serial port. ST CubeMX has a bug with F3 USB code generation, USB DM/DP pins were not configured properly. Add serial commands to start/stop data flow on serial port, show/set sacn interval and read SD card data block.
2016-10-30 | 3.5 | Back to 16G SD card. Make code work with newer larger SD card and compatible with old smaller SD card. Tested with both the 16G SD card comes with TDM board and the old 2G card I have.